## Slide 1
CRM redesign is transitioning from discovery to enterprise delivery, with Methodology now the critical dependency
Top-down platform model confirmed; core document approved; automation built and tested; October rollout planned across Audit.
1 Approach agreed
Execute CRM at the platform level rather than separately at each AU.
Retain regional views where required, including US regulatory requirements.
Design principle: simplify execution without recreating the current AU-by-AU model.
2 Where we are
Standardized CRM document designed and approved at OC level.
Data availability assessed across core pre-population sources.
Data pipeline and AI agent built and tested.
Remaining focus: cross-platform process, Methodology and Change & Adoption.
3 October delivery
New standardized CRM document for all Audit.
Platform-level execution with regional views where required.
Pre-populated content, including AI-generated executive movement summaries with supporting data and logic retained in the appendix.
Redesigned methodology.
4 SteerCo support
Endorse direction and provide feedback on progress.
Escalate with Head of Methodology: this is now the largest dependency to October delivery.
Maintain awareness of delivery risk and decision points.
DELIVERY READINESS BY WORKSTREAM
CRM document
COMPLETE
Discovery
ADVANCED
Process design
IN PROGRESS
Data & analytics
ADVANCED
Methodology
AT RISK
Change & adoption
NOT STARTED
Executive takeaway
The operating model and enabling automation are materially advanced. The primary risk has shifted from solution design to timely Methodology delivery and enterprise change readiness.
Source: CRM transformation discovery and design status

## Slide 2
October delivery moves CRM from fragmented AU execution to a standardized platform + regional operating model
Scope is enterprise-wide; remaining design work is concentrated in teams whose AUs span multiple platforms.
OPERATING MODEL
TODAY | AU-LEVEL CRM
Capital Markets
Global Markets AU
Corporate Banking AU
COO AU
…other AUs
OCTOBER | PLATFORM CRM
Capital Markets CRM
Canada
US
Caribbean
EU
APAC
One platform view; regional views where required
WHAT USERS RECEIVE IN OCTOBER
1
Standardized CRM document
OC-approved document structure applied consistently across Audit.
2
Platform + regional structure
Platform-level execution with regional views embedded where required.
3
Pre-populated evidence
AI-generated executive movement summary plus supporting data and logic in the document appendix.
4
Redesigned methodology
Updated methodology aligned to the new operating model and document.
ENTERPRISE SCOPE
Platform audit teams
Capital Markets
Wealth Management
Personal Banking
Commercial Banking
RBC Bank Georgia
CNB
Technology & Operations
Compliance
GRM
CFO
HR
CLAO
Insurance
Financial Crimes (2nd line)
Regional views are defined by platform and regulatory need (e.g., CM: Canada / US / Caribbean / EU / APAC).
Cross-platform teams — remaining process design
Global Credit Risk
Model Risk
Banking Operations
Financial Crimes (1st line)
Design question: how these teams contribute at platform level without recreating AU-level CRM.
Scope based on current Audit platform structure

## Slide 3
Core build is advanced; Methodology is the primary risk to October delivery
Known September milestones are defined; remaining October milestones are intentionally left undated for completion.
WORKSTREAM READINESS
WORKSTREAM
STATUS
CURRENT POSITION / REMAINING WORK
CRM document
COMPLETE
OC-approved standardized document
Discovery
ADVANCED
Data availability and user insights largely established
Process design
IN PROGRESS
Finalize user journey and cross-platform team model
Data & Analytics
ADVANCED
Pipeline and AI agent built/tested; complete platform validation
Methodology
AT RISK
Methodology changes have not begun; critical path to rollout
Change & Adoption
NOT STARTED
Change strategy, communications and rollout to commence
CRITICAL DEPENDENCY
Methodology changes have not started.
SteerCo ask: endorse the direction and escalate with the Head of Methodology to protect October delivery.
CRITICAL MILESTONES
18 Sep
Process design finalized for all Audit teams; new process communicated; Change Plan ready for Tech & AI SteerCo feedback.
25 Sep
Methodology changes ready for approval; automation validation complete across all platforms.
DATE TBD
Methodology approval confirmed.
DATE TBD
Change & Adoption / user readiness activities completed.
DATE TBD
Production readiness and final pre-populated CRM documents completed.
OCT – TBD
Enterprise go-live across Audit.
Milestones reflect current plan; undated items require confirmation

## Slide 4
Appendix A | Process insights framework
Use this page to capture platform / regional nuances, common patterns and implications for the final operating model.
PLATFORM LENS
PLATFORM
STRUCTURE / NUANCE
REGIONAL REQUIREMENT
OBSERVED PATTERN
DESIGN IMPLICATION
Capital Markets
~13 AUs; globally complex structure
Canada / US / Caribbean / EU / APAC
Most hesitant team to date; concerns on regional model, global consolidation and shared editing
Define explicit regional ownership, global consolidation rules and document collaboration model
Wealth Management
TO COMPLETE
Canada / US / EU / APAC
TO COMPLETE
TO COMPLETE
Technology & Operations
TO COMPLETE
Canada / US / APAC / EU / Caribbean
TO COMPLETE
TO COMPLETE
Other platforms
TO COMPLETE
Per platform
TO COMPLETE
TO COMPLETE
CROSS-PLATFORM / RISK TEAM LENS
TEAM
PLATFORMS CROSSED
OPERATING-MODEL QUESTION
CURRENT DIRECTION / VALIDATION
Global Credit Risk
RBC Bank Georgia, CM, GRM, PB, WM, CB, CNB
How should Credit contribute without recreating AU-level CRM?
Some users favour platform-level commentary; validate with Credit.
Model Risk
PB, CB, CM, WM, GRM, Insurance, CNB, etc.
How should model-risk commentary be incorporated across multiple platform CRMs?
To validate with Model Risk.
Banking Operations
PB, RBC Bank Georgia, CLAO, TO, CB
How should Banking Operations feed platform CRM consistently?
To validate with Banking Operations.
Financial Crimes – 1st line
PB, CM, WM, CNB, RBC Bank Georgia
How should 1st-line FC input be reflected by platform?
To validate.
Framework intentionally retains placeholders for continued discovery

## Slide 5
Appendix B | Data & analysis insights
Assess each source by coverage, rules / thresholds, judgement required and the design implication for standardized pre-population.
SOURCE
CRM USE
COVERAGE
RULE / THRESHOLD
JUDGEMENT?
KNOWN LIMITATION / DESIGN IMPLICATION
Workday
Executive / org movements
Platform mapping assessed
Logic-based
Some
Supports AI-generated executive-level movement summaries; final relevance still requires auditor review.
PRAM
Projects / contracts
Platform availability assessed
No objective threshold
Yes
Cannot reliably identify “key business initiatives” from source data alone; management discussion remains necessary. Consider contracts as well as projects.
ORE
Operational risk events
Platform / region mapping assessed
Yes
Limited
Include OREs closed in-quarter as well as net-new OREs; threshold can support standardization.
Audit Issues
Relevant audit issues
Platform-relevant logic
Platform logic
Some
Use platform-relevance logic rather than a universal quantitative threshold.
MSI Issues
Management self-identified issues
TO COMPLETE
TO COMPLETE
TO COMPLETE
TO COMPLETE
MetricStream
TO COMPLETE
TO COMPLETE
TO COMPLETE
TO COMPLETE
TO COMPLETE
EIM
TO COMPLETE
TO COMPLETE
TO COMPLETE
TO COMPLETE
TO COMPLETE
Known mapping gap
RBC Bank Georgia is not readily identifiable in current pre-population sources.
Emerging design principles
1 Automation should support — not replace — auditor judgement • 2 Standardization does not require one universal numeric threshold • 3 Data availability ≠ decision sufficiency
Data-source assessment reflects current discovery; RegComp remains a candidate source to assess

## Slide 6
Appendix C | Audit teams engaged to date
Engagement spans Audit leadership, platform / regional teams and risk functions; remaining discussions focus on cross-platform operating-model questions.
COMPLETED ENGAGEMENT
Leadership / platform coverage
CAE OC
CAE ELOC
US SMT
WM & INS / US WM
US CM / CM
EU & APAC
AML
US Risk Mgmt / Op Risk Mgmt
GRM
CFO / HRBMCC / CLAO / GC
US TO / TO
PB & CB
Coverage objective: validate the platform-level process, regional implications, data usability and cross-platform team interactions.
WEEK OF 14 SEP
Next wave
Banking Operations & Credit
Model Risk
CNB
STEERCO DISCUSSION
RBC Bank Georgia
Requires discussion with Tech & AI SteerCo, including how RBCB is represented in the platform model and current data-source mapping.
Engagement status as of 13 Sep 2026