## Slide 1
01 | Audit team engagement & feedback
Broad engagement completed; remaining validation targeted for week commencing 14 September
ENGAGED
CAE OC • CAE ELOC • US SMT • WM & INS / US WM • US CM / CM • EU & APAC • AML • US Risk / Op Risk • GRM • CFO / HRBMCC / CLAO / GC • US TO / TO • PB & CB
NEXT WAVE
BO & Credit • Model Risk • CNB • RBCB*
* RBCB to be tabled for Tech & AI SteerCo discussion
WHAT WE ARE HEARING
01
Positive overall
Broad support for the proposed CRM process change.
02
Global consolidation
Questions remain on how a regional model consolidates into global CRM.
03
Shared editing
Some hesitation around multiple users / teams editing the same document.
04
Non-platform input
Some teams prefer Credit / Model Risk commentary to be added at platform level.
AREA REQUIRING MOST VALIDATION
Capital Markets
CM — particularly outside the US — has shown the most hesitation. Its global complexity and ~13-AU structure creates additional questions around regional ownership and global consolidation.
SteerCo focus: confirm whether any feedback requires a design change or targeted follow-up before process design is locked.
1

## Slide 2
02 | CRM data assessment: observations & potential gaps
Early findings from datasets being incorporated into CRM pre-population
DATASET / AREA
OBSERVATION
IMPLICATION / NEXT STEP
ORE
ORE analysis should include items closed during the quarter as well as net new OREs.
Confirm scope and calculation logic.
EDS / PRAM — initiatives
Consensus is that objective criteria are insufficient to identify key business initiatives; these are primarily identified through management discussion.
Use data to inform discussion, not replace judgement.
PRAM — contracts
In addition to projects, contracts may provide useful CRM context.
Assess value and extraction feasibility.
RBCB
RBCB is not easily identifiable in the data sources currently used for pre-population.
Resolve platform mapping / source coverage.
RegComp dashboard
Potential source for regulatory issue information at platform level.
Assess accessibility, granularity and integration feasibility.
EMERGING THEMES
Coverage & mapping • Completeness • Granularity • Source integration • Management judgement
Key question: where should CRM retain judgement / manual input versus invest in additional data sourcing or integration?
2