## Slide 1
CONTINUOUS RISK MONITORING · PROCESS TRANSFORMATION
Auditor persona workflow
How Regional IA, the Platform CRM owner, Analytics, and Approvers
move one CRM object — without four Word files.
Worked example: Wealth Management · APAC · UK · US · CAN · FQ4 2026

## Slide 2
PERSONA WORKFLOW
Four personas, one CRM object — swimlane
CRM auditor workflow · Wealth Management pilot
2 / 5
Regional IA
US · UK · CAN · APAC
Owns local facts
Platform CRM
owner
Owns synthesis
Analytics /
AuditIQ
Owns the object
Approver
AU / RA / plan only
1. Confirm freeze
KRIs, issues, exams, PAR rows pre-loaded. No typing.
2. Structured checklist
45–90 min. Scope + status taxonomy + so-what.
3. Propose deltas
AU / RA / plan only if residual moved.
4. ½-page narrative
Exceptions only. Inherit Global rows.
5. Completeness pass
Every region checked in. Challenge missing tags.
6. Apply view rules
Platform-brief Y/N. Collapse same-theme items.
7. Write SOTU
Only Y items. Accept / reject plan deltas.
8. Publish views
Platform brief + 4 regional cuts + heatmap.
Pre-populate CRM object from source systems
Issues · plan · PAR · KRI dashboard · exam log · last-quarter brief
Generate drafts + enforce taxonomy
Closed lists. No-change cells cannot receive paragraphs.
Write accepted deltas to Auditsphere
AU residual, plan timing, advisory adds — once, not four times.
Approve only AU / RA / plan changes
US Advice pull-forward this quarter. Quiet regions do not enter this lane.
Do not reuse the platform chain on regional views
Regional prepared + regional reviewed is enough unless the item changes AU, RA, or the plan.

## Slide 3
PERSONA · REGIONAL IA
A quarter in the life of the US Wealth Management auditor
CRM auditor workflow · Wealth Management pilot
3 / 5
W1 Freeze
Read only
W2 Checklist
45–90 min
W2 Propose
If residual moved
W3 React
Challenge only
W3–W4 Sign
Prepared
Open the US filter
CRM-WM-2026-Q4 already holds pre-loaded KRIs, issues, PAR, exams. Confirm the freeze. Do not export to Word.
Tag what you own
New US COO. Retirement onboarding $2.4M. Reg BI exam. Advice-fail 5.2%. Status taxonomy is a dropdown.
One plan proposal
Residual ↑ on WM–Advice–US. Propose pull-forward of 2027 suitability engagement. Stop. Platform owner decides.
Do not rewrite Global
CIO appointment, advisor desktop, enterprise cyber already exist as Global rows. Confirm US impact flag only.
Half page, then Prepared
Generator drafts the US view. Edit judgment sentences. Sign Prepared — US tagged facts only.
What the US auditor stops doing
No SOTU rewrite
Platform owner writes the left-hand page from tagged bullets.
No “no change” essays
UK/CAN quiet steps are a status code. They never become paragraphs.
No second cyber issue
Enterprise finding is one record with US = Impacted.
No KRI re-key
Confirm the dashboard value. Attach WM-QA-Q4. Move on.
No four-person approve
US Prepared is enough until AU/RA/plan moves — which it did, once.
No parallel Word file
The US view is a filter on CRM-WM-2026-Q4.

## Slide 4
PERSONA · PLATFORM CRM OWNER
The WM platform lead synthesizes — they do not re-type
CRM auditor workflow · Wealth Management pilot
4 / 5
01
Gate the intake
W2 cannot close until all four regions have a Prepared stamp or an explicit “nothing material” status on every step.
02
Run the view rules
Generator applies VR-01 to VR-12. You only override platform_brief_flag when judgment disagrees with the rule.
03
Collapse or split themes
UK Duty + US Reg BI = one control theme (advice evidence). Do not invent a third “platform culture” theme.
04
Decide the three writes
Accept US residual ↑ and plan pull-forward. Accept UK advisory. Reject anything that would create a fourth WM platform.
05
Write eight bullets max
SOTU is the only free-text you author. Everything else is a table filtered from facts.
06
Publish three artifacts
Platform brief (current look). Four regional cuts. One heatmap. Same object ID on every footer.

## Slide 5
DECISION RIGHTS
Who is allowed to touch which field
CRM auditor workflow · Wealth Management pilot
5 / 5
Field / decision
Regional IA
Platform owner
Analytics
Approver
Create regional FACT
Yes
Completeness only
Pre-load
—
Create Global FACT
No — request
Yes
Pre-load
—
status_taxonomy up to CHG_NO_IMPACT
Yes
Spot check
Enforce list
—
status_taxonomy CHG_RA / CHG_PLAN
Propose
Accept / reject
Write if accepted
Yes
platform_brief_flag override
Suggest
Yes
Default from rules
—
SOTU narrative
3–5 bullets max
Author
Draft from facts
—
Regional ½-page
Author
Challenge
Draft
Regional lead
Auditsphere AU / RA / plan write
Propose
Decide
Execute write
Countersign