## Slide 1
Model Risk input across platform CRM documents
PROPOSED WORKFLOW
FOR VALIDATION
Existing AUs define contribution scope; Model Risk reviews shared evidence and adds platform-specific input.
AU coverage → Platform + relevant regional views → Targeted Model Risk input | No duplicate AU-level CRM
1
Generate
platform packs
2
Map AU
coverage
3
Assign owners
& hand-offs
4
Validate
base content
5
Review Model
Risk evidence
6
Add platform
commentary
7
Cross-platform
review
8
Sign off
& submit
Central CRM /
Data & AI
Shared evidence
Platform
audit teams
Validate shared
platform content
Model Risk
audit team
Review and
contribute
Platform CRM
documents
Input follows
AU coverage
Output /
governance
Pull WorkDay, PRAM, ORE and MS/EIM evidence.
Pre-populate platform / regional packs with an AI summary of executive movements and supporting evidence / logic.
Shared evidence is available to both platform and Model Risk teams
Platform teams own the shared baseline;
Model Risk does not rebuild it.
04 | Validate shared platform content
Confirm relevance, regional coverage and missing context; complete the platform-owned narrative.
07 | Review Model Risk input
Resolve comments and confirm document readiness.
02 | Map existing AU coverage
Link AUs to platform CRM documents and relevant regional views. Review only platforms in scope.
03 | Assign owners
Name one Model Risk contributor per platform. Agree editing hand-offs.
05 | Review, do not re-create
Review model developments, issues and events in the pack. Use management input to close evidence gaps.
06–07 | Draft and cross-check input
State platform implications and regional nuance. Compare themes across platforms; reuse evidence, not identical conclusions.
Capital
Markets
Model Risk input
Personal
Banking
Model Risk input
Commercial
Banking
Model Risk input
Wealth
Management
Model Risk input
GRM
Model Risk input
Insurance
Model Risk input
CNB
Model Risk input
Common fields: changes / issues · platform impact · regional nuance · evidence links · “No material update”, where applicable
Illustrative platform set; exact documents and regional views follow confirmed Model Risk AU coverage.
Model Risk confirms its contribution
Evidence and regional implications checked.
Platform team resolves final comments
Common themes retain platform-specific context.
Platform owner signs off and submits
Final pack includes Model Risk input and appendix.
USER EXPERIENCE
Less duplicate preparation
Targeted analysis
Clear contribution ownership
Fewer editing conflicts
CRM TRANSFORMATION | Proposed workflow: ownership, contribution fields and hand-offs remain subject to validation.
1
Notes: MODEL RISK AUDIT TEAM – PROPOSED PLATFORM CRM CONTRIBUTION JOURNEY
Purpose
Reduce time spent on CRM data preparation and analysis while making contribution to multiple platform documents straightforward. This is an editable rendering of the detailed process diagram discussed with Daniel, not a statement that all workflow arrangements have already been approved.
Agreed design context from the discussion
• CRM moves from AU-level execution to platform-level execution, retaining regional views as required.
• The standardized CRM document has been designed and approved at OC level.
• Parts are pre-populated from WorkDay, PRAM, ORE and issues data (MS/EIM). The described AI example is a summary of executive-level movements, with supporting evidence and logic in the appendix.
• Model Risk has AUs spanning multiple platforms. Its existing AU coverage determines which platform documents and regional views require its contribution. The seven platforms shown are illustrative examples provided in the discussion, not a complete or finalized AU-to-region mapping.
Eight-stage journey
1. Central CRM / Data & AI prepares shared platform and regional packs and evidence once.
2. Model Risk maps its existing AUs to the relevant platform CRM documents and applicable regional views. Platforms with no relevant coverage are excluded from the routine contribution list.
3. Model Risk assigns a contributor for each relevant platform, agrees the contribution scope and editing hand-off with the platform team, and uses a consistent contribution structure.
4. Platform teams validate the common baseline, source relevance and regional coverage, flag missing context and complete the platform-owned narrative.
5. Model Risk reviews relevant platform evidence for model developments, issues and events instead of reconstructing data analysis. It seeks targeted management discussion where the sources cannot adequately answer the question.
6. Model Risk contributes within every relevant platform CRM document. Proposed contribution fields are changes/issues, platform implications, regional nuances and supporting evidence links; where applicable, explicitly record no material update.
7. Model Risk compares patterns across its platform contributions, checks consistency, and retains the specific implications for each platform. Platform teams review Model Risk input and resolve comments. A separate consolidated Model Risk perspective may be useful internally but must not create a duplicate mandatory AU-level CRM product.
8. Model Risk confirms its contribution, the platform team resolves final comments, and the proposed platform owner signs off and submits the final platform pack with supporting evidence and logic.
User experience / workflow design
• Use common evidence and a common response structure rather than ask Model Risk to rebuild preparation for every AU.
• AU mapping determines contribution destinations; it must not recreate one CRM document per AU.
• Existing AUs can remain the coverage traceability mechanism; this diagram does not assume an AU inventory change.
• Agree clear section-level contribution ownership and hand-offs. Do not unnecessarily serialize all platform work or assume that whole-document locking is required.
• Model Risk scoping and allocation can proceed while platform teams validate the common baseline.
• Reuse evidence and common themes where appropriate, not identical conclusions across unrelated platforms.
Validation still required
The exact AU-to-platform/region mapping, contribution fields, reviewer allocation, editing arrangements, global/regional consolidation and sign-off responsibilities must be validated with Model Risk, platform teams and Methodology. No new system functionality, committed time saving or additional source-data coverage is asserted by this diagram.
Source: user-provided CRM redesign information and the detailed user-journey image in this conversation.